## Scoping Template
QuickSight Launch offering scoping template | Steps to use this tempalte: | Color Coding of the cells
| 1. Collect info from the customer to ill three estimates sheets; | Cells to fill manually
Purpose: this scoping template is designed to help ProServe sellers to collect information from customers, and provide a good faith estimate to customer for QuickSight projects | 2. Make manual adjustments; | Cells calculated automatically
| 3. Total estimated hours is generated automatically. | Final results
Breakdown Satges of scoping
Fill 1 or 0 below
QuickSight account configuration (Optional if the account is ready) estimate sheet | Estimated Hours per task | 1 for task exists, 0 for tasks not exist | Hours
Account configuration: subscription, VPC Configuration for data source, SPICE capacity planning and etc.. | 16 | 1 | 16
User management of QuickSight | 24 | 0 | 0
Total Configuration Hours |  |  | 16
This section is Q align offering scoping estimation template
Discover the linkege between Questions and Data estimate sheet | Fill numbers below
Number of Questions | 16
Number of data sources | 2
Number of tables per data source | 10
Number of fields per table | 10
Total Data Modeling Hours | 54
Fill 1 or 0 below
Security Design and Implementation (Optional if the security architecture is ready) estimate sheet | Estimated Hours per task | 1 for task exists, 0 for tasks not exist | Hours
Implement new SSO service | 40 | 1 | 40
AD integration | 40 | 0 | 0
Integrate with existing SSO service | 20 | 1 | 20
Programmable QuickSight User/Group provision | 40 | 0 | 0
Total Security Hours |  |  | 60
Fill 1 or 0 below
Datasets Creation estimate sheet | Estimated Hours per task | 1 for task exists, 0 for tasks not exist | Hours
DB views/new tables creation | 40 | 0 | 0
QuickSight Datasets | 40 | 1 | 40
Dataset refresh pipeline | 20 | 1 | 20
Programmable ETL and QuickSight dataset refresh | 80 | 0 | 0
Total Security Hours |  |  | 60
Topic Implementation estimate sheet |  | Fill numbers below
| Number of topics | 2
| Average fields per topic | 50
| Average filter per topic | 10
Average custom cell values per topic
| Average name entities per topic | 5
Total topic implementation Hours |  | 130
Item | Suggested Hours | Manual Adjustments | Actual Hours
Requirements confirmation, sample questions study, architectual design, UX guideline | 40 | 0 | 40
Account configuration (environment setup) | 16 | 0 | 16
Discover the linkege between Questions and Data estimate sheet (Please fill the estimate sheet above) | 54 | 0 | 54
Security Design and implementation (Please fill the estimate sheet above) | 60 | 0 | 60
Dataset creation implementation (Please fill the estimate sheet above) | 60 | 0 | 60
Topic implementation (Please fill the estimate sheet above) | 130 | 0 | 130
UAT test: run the questions, build dashboard to run data validation and etc.. | 20 |  | 20
Embedded topic | 40 | 0 | 40
Assist prod migration, testing, knowledge transfer, hand over | 80 | 0 | 80
Total |  |  | 500

## Timeline sample
Stage | Actions | Resource | Time (Hrs)
Account set up, Discover the linkege between Questions and Data | Study the questions | Sr. Consultant | 16
| Study the schema of the tables | Sr. Consultant | 24
| Build the map between the DWH fields and intents in questions | Sr. Consultant | 24
| Define design of fields, filter, entities of Q topic. | Sr. Consultant | 16
| QuickSight account configuration (Optional if the account is ready) | Staff. Consultant | 8
| User management of QuickSight (Optional if the user/group is ready) | Sr. Consultant | 16
| Security Architecture: VPC, RLS and etc.. (Optional if the data source is ready) | Sr. Consultant | 16
| subtotal |  | 120
Data Modeling | Build DB views | Staff. Consultant | 32
| Build DB views | Sr. Consultant | 8
| Build QuickSight datasets | Staff. Consultant | 40
| Build QuickSight datasets | Sr. Consultant | 8
| Data pipeline | Staff. Consultant | 8
| subtotal |  | 96
Q topic building | Create fields, entities, filters and etc.. | Staff. Consultant | 24
| Create fields, entities, filters and etc.. | Sr. Consultant | 8
| UAT test: build dashboard to run data validation | Staff. Consultant | 16
| Topic refinement | Sr. Consultant | 8
| Topic refinement | Staff. Consultant | 16
| subtotal |  | 72
Product release | Migrate from non-prod to prod | Staff. Consultant | 16
| Embedded Q search bar into web portal | Sr. Consultant | 16
| subtotal |  | 32
| Total |  | 320

## Questions
Question | Category | Type
What is the total number of patients enrolled at MGB for asthma? | adoption | descriptive
What is the demographic profile of asthma patients at GAA? | adoption | descriptive
How many new patients were enrolled for heart failure at MGB yesterday/last week/in September? | adoption | descriptive
What is the percentage of active users at MGB? | engagement | descriptive
How many messages are patients sending to clinicians on a daily basis? | engagement | descriptive
What is patient engagement over time measured by daily logs submitted? | engagement | descriptive
How many ( or percentage) heart failure patients at MGB are being treated with SGLT2i/Farxiga? | treatment | descriptive
What is the trend of reported KCCQ scores for heart failure patients at MGB? | outcome | descriptive
What is the trend of total patient count at GAA for the next 3 months? | adoption | predictive
What are the engagement levels of asthma patients based on how well the condition is managed (ACT)? | engagement | descriptive