## QS Greenfield Scoping
QuickSight Launch offering scoping template | Steps to use this tempalte:
| 1. Collect info from the customer to ill three estimates sheets; | Cells to fill manually
Purpose: this scoping template is designed to help ProServe sellers to collect information from customers, and provide a good faith estimate to customer for QuickSight projects. Include/exclude: This template only contains ProServe hours estimation. For QS license cost, please refer to https://aws.amazon.com/quicksight/pricing/ | 2. Make manual adjustments; | Cells calculated automatically
| 3. Total estimated hours is generated automatically. | Final results
Note: Q scoping template is here
For non-proserve user, Q template is here
Item | Suggested Hours | Manual Adjustments | Actual Hours
Requirements confirmation, architectual design, UX guideline | 40 | 0 | 40
Architectual implementation, environment setup | 40 | 0 | 40
DWH and SPICE Data modeling (Please fill the estimate sheet below) | 64 | 0 | 64
Security Design and implementation (Please fill the estimate sheet below) | 100 | 0 | 100
Dashboard implementation (Please fill the estimate sheet below) | 405 | 0 | 405
CICD (BIOps) design and implementation (Please fill the estimate sheet below) | 140 | 0 | 140
Admin Console solution to monitor usage metrics | 80 | 0 | 80
Embedded dashboard | 80 | 0 | 80
Testing, knowledge transfer, hand over | 80 | 0 | 80
Total |  |  | 1029
Data Modeling estimate sheet | Fill numbers below
Number of data sources | 2
Number of tables per data source | 10
Number of fields per table | 10
Number of datasets for Incremental refresh design | 20
Number of datasets for Composite SPICE design | 40
Total Data Modeling Hours | 64
Fill 1 or 0 below
Security Design and Implementation estimate sheet | Estimated Hours per task | 1 for task exists, 0 for tasks not exist | Hours
Implement new SSO service | 40 | 1 | 40
AD integration | 40 | 0 | 0
Integrate with existing SSO service | 20 | 1 | 20
Programmable QuickSight User/Group provision | 40 | 0 | 0
RLS design (integrate with users information from data base) | 40 | 1 | 40
Total Security Hours |  |  | 100
Dashboard Implementation estimate sheet |  | Fill numbers below
| Number of dashboards | 2
| Average sheets per dashboard | 5
| Flexible layout? Yes=1.5, No=1 | 1.5
Dashboard Complexity index | Input 1 if per dashboard there are 5-10 visuals, no complex calculated fields, no rls | 1.5
Input 2 if per dashboard there are 10-20 visuals, or complicaed calculated fields, or rls
Input 0.6 if per dashboard there are less than 5 visuals
Input between 0.6 ~ 2 after reviewing the dashboard design, based above description
Total dashboard implementation Hours |  | 405
Fill 1 or 0 below
CICD BIOps estimate sheet | Estimated Hours per task | 1 for task exists, 0 for tasks not exist | Hours
CLI training and sample bash scripts POC | 20 | 1 | 20
SageMaker Notebooks | 40 | 0 | 0
CDK solution with UI | 120 | 1 | 120
Total BIOps Hours |  |  | 140